## Agile Product Backlog
AGILE PRODUCT BACKLOG
STORY ID | PRIORITY | TYPE | ITEM | SP | STATUS
1 | High | Story | As a System administrator I want to manage a user to administer the system | 5 | Not Started
2 | Low | Story | As a System administrator I want to assign username and password to users to allow the login to the platform | 2 | Not Started
3 | High | Story | As a System administrator I want to assign a role to user to manage the staff | 2 | Not Started
4 | Medium | Story | As a System administrator I want to assign skills to maintainers to choose the right maintainers | 2 | Not Started
5 | Low | Story | As a System administrator I want to associate each maintaier with a procedure that must be carried out for a certain maintenance activity | 2 | Not Started
6 | Low | Story | As a System administrator I want to manage Workspace notes to track useful information | 3 | Not Started
7 | Low | Story | As a system administrator i want to view the accesses to check the login history | 1 | Not Started
8 | Medium | Story | As a System administrator I want to manage a general list of skills to help the planner choose the maintainer with required skills | 3 | Not Started
9 | High | Story | As a Planner i want to manage maintenance activities to organize the work | 8 | Not Started
10 | Medium | Story | As a Planner i want to view the maintenance activities sorted by weeks to better split out the work | 5 | Not Started
11 | High | Story | As a planner i want to choose which activity to start so i can have all the necessary informations | 2 | Not Started
12 | High | Story | As a planner i want to see the maintainers availabilities to check the days in which they're not busy | 13 | Not Started
13 | High | Story | As a Planner i want to assign activity to a maintainer according to his disponibility and capacity so i can choose the most fit to the activity | 8 | Not Started
14 | Medium | Story | As a planner i want to manage an EWO so i can manage the staff needed to resolve the issue | 5 | Not Started
15 | Low | Story | As a planner i want to manage the materials needed for the maintenance activity so i can help the maintainers with his work | 3 | Not Started
16 | Medium | Story | As a Planner i want to view the state of each EWO so i can check the progress | 5 | Not Started
17 | Medium | Story | As System Administrator i want to manage sites and areas of the factory so i can simplify the activity management | 5 | Not Started
18 | Low | Story | As a System Administrator i want to manage a list of materials so i can control the materials used to do the maintainaince | 3 | Not Started
19 | Low | Story | As a System Administrator i want to manage a list of maintenance procedures so i can standardize maintenaince activities | 3 | Not Started
20 | Medium | Story | As a System Administrator i want to assign competences to activities so i can find the most fit maintainer | 5 | Not Started
21 | Medium | Story | As a System Admnistrator i want to manage the activity types so i can simplify the search for the required skills | 5 | Not Started